## Tabelle1
8-Weeks_Project Milestones
| Mon | Tus | Wed | Thu | Fri | Milestones
July |  | 15 | 16 | 17 | 18 | Milestone 1: Research and study, sketch system design, design 3D holders and printing, hardware implementation.
| 21 | 22 | 23 | 24 | 25
| 28 | 29 | 30 | 31 | 1 | Milestone 2: Coding each Raspberry Pi and testing real-time data for lane keeping.
Aug | 4 | 5 | 6 | 7 | 8
| 11 | 12 | 13 | 14 | 15 | Milestone 3: V2V communication and safety driving testing.
| 18 | 19 | 20 | 21 | 22
| 25 | 26 | 27 | 28 | 29 | Milestone 4: Go live, documentation, and presentation.
Sep | 1 | 2 | 3 | 4 | 5